## Product Backlog
User Story | Title | Description | Acceptance Criteria (most important) - limitations, details of the information, etc | User Story Points | Priority | Assigned To | Which Sprint | Completed? | Carried Over From Sprint | Remarks
1 | Account Enquiry | As a customer, I want to ask general questions about my bank account so that I can understand my account information and services, without having to call of visit a branch | General Account Questions - The bot answers general, non-personal questions about account features, fees, limits, interest, and services without requiring login. - Answers come from approved product and fee information, and are written in plain language. - The bot understands common phrasings and follow-up questions in the same conversation. - If the bot cannot answer, it says so and offers a link to the relevant help page or a person. - The bot is available in the customer's preferred language. - A "Talk to a person" option is available at any point. Personal Account Information - Before showing any account-specific information, the bot asks the customer to log in or complete secure authentication. - Once authenticated, the bot can answer questions about balances, recent transactions, account details, and fees charged. - The bot can explain a specific charge or transaction in plain language (e.g. what a fee is for). - Sensitive details such as full account numbers are masked by default. - The customer can ask follow-up questions without re-authenticating during the same session, until the session times out. - Account information shown matches the banking system of record. Service and Product Guidance - The bot explains available services (e.g. cards, transfers, statements, online banking features) and how to use them. - Where relevant, the bot gives step-by-step guidance or links directly to the right place in the app or website. - The bot does not give personalized investment, legal, or tax advice, and states this when asked. - If the customer needs something the bot can't do (e.g. closing an account or disputing a transaction), it hands over to a person or the right service channel with the conversation context. |  |  | Denise
2 | Loan Enquiry | As a customer, I want to ask about available loan products, eligibility requirements and application procedures so that I can understand my borrowing options. | • Explains loan types, eligibility, application steps, based on the customers' existing profile (this helps them to efficiently filter out loans that they are eligible for) • Unless the customer specify what they are looking out for in a loan • Never promises or implies approval • States bank makes final decision • Refers to staff for own application Limitation: • General info only
3 | Credit Card Enquiry | As a customer, I want to ask questions about my credit card, such as fees, limits and payment due dates, so that I can manage my card properly. | • Explains fees, limits, due dates in general terms • Cannot help to see own statement – instead says where and how to find it • Uses facts only from agreed info source • Otherwise says 'check official terms'
4 | Transaction Issue | As a customer, I want to ask about failed, pending or unfamiliar transactions so that I can understand the issue and know what to do next. | • Explains failed vs pending vs unfamiliar in plain words • Gives clear next steps for each • Anything unfamiliar = possible fraud → contact bank immediately • Cannot look up or reverse real transactions • Otherwise, asked to contact
5 | Banking Service Information | As a customer, I want to ask about common banking services and procedures so that I can get help without contacting a customer service officer. | • Answers common 'how do I…' questions • Only from agreed info source • Never invents details • Redirects off-topic questions politely
6 | Natural Language Query | As a customer, I want to describe my banking question in natural language so that I can receive a relevant response without using specific banking terms. | • Understands everyday wording and typos • Handles vague questions (e.g. 'my card not working') • Same answer when question is rephrased • No banking jargon needed from customer
7 | Compliance reviews | As a client with a compliance document request, I want the chatbot to explain in plain language why each document and regulation applies and guide me through resolving it, so that I can provide the right documents first time and avoid my account being delayed or frozen. | - Given a client has an open document request, when they ask why it's needed, the bot explains the purpose in plain language (target reading level, e.g. grade 8) and references the relevant regulatory driver (e.g. MAS or FINMA requirement). - The explanation is tailored to the client's booking centre and jurisdiction. - The bot lists accepted document types and examples of what "good" looks like. - Explanations come from a compliance-approved content library, not free-form generation, so regulatory statements are accurate and auditable. - If the client's question falls outside approved content, the bot escalates to a relationship manager or compliance contact. - Supports the client's preferred language.
8 | AI-Assisted Document Pre-Verification | As a client submitting supporting documents, I want to upload them securely in the chat and get immediate feedback on whether they're acceptable, so that I can fix problems right away instead of waiting days for a rejection. | - Client is authenticated (step-up authentication) before the upload option appears. - Files upload over encrypted channels, with supported formats and size limits stated up front. - OCR checks run automatically for: legible text, visible issue/statement date within the required window, signature present where required, and name/entity matching the client record. - If a check fails, the bot states which check failed and what to do (e.g. "The statement date is older than 3 months. Please upload a more recent one."). - If all checks pass, the document is routed to the compliance officer queue, tagged "pre-screened", with the check results attached. - The bot is clear that pre-screening is not final approval; the compliance officer makes the decision. - Documents are stored and retained per UBS data-residency and retention policy, and every upload and check result is logged for audit.
9 | Compliance Milestone Tracker | As a client waiting on a compliance review, I want to see a visual progress tracker showing where my review stands, so that I know what's happening, what's pending from me, and roughly when to expect an outcome. | - Tracker displays defined stages (e.g. Request received → Documents submitted → Pre-screened → Under officer review → Decision). - Current stage, completed stages, and any action required from the client are visibly highlighted. - Status updates are triggered by actual case-management system events, not manually. - Client receives a notification (in-app/email, per preference) on stage changes. - Shows an estimated timeframe where available, with wording that avoids hard promises. - Tracker never reveals sensitive internal details (e.g. AML risk scoring or suspicion indicators) that could constitute tipping-off. - A "Talk to a person" option is available from every screen.
10 | Smooth relationship manager transition | As a client whose advisor has been changed, I want to be introduced to my new advisory team in a personal, timely way, so that I know who is looking after me and feel the relationship is continuing. | - Given a client's advisor has left or been reassigned, when the change is recorded, the bot triggers a personalized onboarding sequence. - The sequence introduces the new advisory team with names, roles, and a short embedded video bio for each member. - The client can reply, ask questions, or request a call directly from the introduction. - The message is delivered in the client's preferred language. - A "Talk to a person" option is available throughout.
11 | Shared Context Summary | As a client moving to a new advisor, I want to review and approve a summary of my preferences before it's handed over, so that I don't have to repeat myself to my new advisor. | - The bot generates a "relationship brief" covering preferred communication frequency, risk tolerance, and past notes. - The client can review each item, edit it, or flag it as incorrect before approving. - Once approved, the brief is sent to the new advisor and attached to the client record. - The client receives confirmation that the brief has been shared. - Access to the brief requires secure authentication.
12 | Instant Meeting Scheduling | As a client with a new advisor, I want to book an alignment call directly in the chat, so that I can quickly reconnect with a person and feel the relationship is secure. | - The bot shows the new advisor's available time slots. - The client can select a slot and choose a call or video meeting. - The booking is added to the advisor's calendar, and both parties receive a confirmation and reminder. - Time zones are handled correctly for both parties. - The client can reschedule or cancel from the chat.
13 | Multi-turn Conversation | As a customer, I want the chatbot to remember what I said earlier in the chat so that I do not have to repeat myself. | • Remembers earlier messages in same chat • Handles follow-ups (e.g. 'what about the other one?') • Does not mix up topics • Forgets everything when chat ends Allowing customers to come back to the chatbot again wherever they left off in the last conversation |  | Medium
14 | Privacy & Security | As a customer, I want the chatbot to never ask for my sensitive login details so that my account stays safe. | • Never asks for PIN, password, OTP, CVV, full card number • Warns customer not to share them • Does not repeat sensitive data back • Tells customer to ignore anyone asking for them in chat |  | High
15 | Transparency & Disclaimers | As a customer, I want to know I am talking to an AI and that answers are general information so that I do not mistake it for official advice. | • States it is an AI at start of chat • Says info is general, not advice or a contract • Disclaimer shown on loans and fees |  | High
16 | Lost or Stolen Card | As a customer, I want to know what to do if my card is lost or stolen so that I can protect my money quickly. | • Gives urgent steps first • Tells customer to contact bank immediately • Cannot block the card itself • Calm, clear tone This can be a backup route where customers can utilise when there is a huge call traffic, to utilise time well when matter is time-sensitive and urgent
17 | Tuning | As the team, I want to improve the bot using test results so that answers get better. | • Review failed tests • Adjust instructions / prompts • Re-test and record improvement • Keep a change log
18 | Explainable Answers | As a customer, I want to see where an answer came from so that I can trust it. | • Shows source of info (e.g. FAQ / help page) • Gives short reason when declining • Source matches the answer given • Can choose to show when asked, so as to not overwhelm customers with extra information they do not need now

## Story points evaluation
All estimations were made using planning poker with the Fibonacci scale.
Sprint 1 | [5 empty] | Summary | Story points | Remarks
User story | Sprint 1 Planning story point | Final story points | Remarks |  |  | Sprint 1 Sprint Planning Total story points | 170
1 | 2 | 2 |  |  |  | Sprint 1 Finished story points | 36
2 | 5 | 5 |  |  |  | Sprint 2 Sprint Planning Total story points | 124
3 | 5 | 5 |  |  |  | Sprint 2 Finished story points
4 | 13 | 13 |  |  |  | Sprint 3 Sprint Planning Total story points
5 | 5 | 5 |  |  |  | Sprint 3 Finished story points
6 | 3 | 3
7 | 3 | 3
Sprint 2
User Story | Sprint 1 Planning story point | Sprint 2 Planning story point | Final story points | Remarks
8 | 13 | 8 | 8
9 | 5 | 5 | 5
10 | 3 | 3 | 3
11 | 13 | 8 | 8
12 | 5 | 5 | 5
13 | 3 | 3 | 3
14 | 5 | 5 | 5
Sprint 3
User Story | Sprint 1 Planning story point | Sprint 2 Planning story point | Sprint 3 Planning story point | Final story points | Remarks
15 | 5 | 5
16 | 5 | 5
17 | 5 | 5
18 | 3 | 3
19 | 3 | 3
20 | 3 | 3
21 | 5 | 5
22 | 5 | 5
23 | 13 | 13
24 | 13 | 13
25 | 3 | 3
26 | 3 | 3
27 | 3 | 3
28 | 8 | 8
29 | 5 | 5
30 | 5 | 5

## Burndown Chart
Sprint | Planned Story Points | Completed Story Points | Expected Cumulative Remaining Story Points | Scope Change | Actual Remaining (end of this sprint) | Ideal Remaining | Cumulative Completed | Final Remaining | Start Backlog
0 | 170 | 0 | 170 | 0 | 170 |  | 0
1 | 170 | 36 | 134 | -10 | 144 | 0 | 36 | 124 | 170
2 | 124
3

## JAMIE Keep single baseline (hidden)
Sprint | Planned Story Points | Completed Story Points | Remaining Story Points | Ideal Remaining | Cumulative Completed | Cumulative Remaining | Total Scope | Final Remaining
1 |  |  | 0 | 96 | 0 | 96 | 96 | 96
2 |  |  | 0 | 96 | 0 | 96
3 |  |  | 0 | 96 | 0 | 96
3.5 |  |  | 0 | 96 | 0 | 96

## JAMIE Track live backlog (hidden)
Sprint | Planned Story Points | Completed Story Points | Remaining Story Points | Ideal Remaining | Cumulative Completed | Cumulative Remaining | Total Scope | Final Remaining | Start Backlog
1 |  |  | 0 | 124.7143 | 0 | 0 | 97 | 97
2 |  |  | 0 | 152.4286 | 0 | 0
3 |  |  | 0 | 180.1429 | 0 | 0
3.5 |  |  | 0 | 194 | 0 | 0

## Copy of Burndown Chart (hidden)
Sprint | Planned Story Points | Completed Story Points | Remaining Story Points | Ideal Remaining | Cumulative Completed | Cumulative Remaining | Total Scope
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0